## SECTION_TIMELINE_MV
SECTION_ID | CELL | EVENT_DATE | EVENT_DESCRIPTION | EVENT_COMMENTS
1-D-1991 | 1 | 08/13/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1103+32.5
1-D-1991 | 1 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
1-P-1991 | 1 | 04/04/1998 | Crack Sealing | """Crafco 522 sealant used with a 3/4"""" route. Comparison Cell-3."""
1-D-1991 | 1 | 07/06/2006 | Section Ends | Replaced with Section(s) 1-D-2006
1-P-1991 | 1 | 06/26/2012 | Section Ends | Replaced with Section(s) 1-P-2012
1-D-2012 | 1 | 07/25/2017 | Section Ends | Replaced with Section(s) 101-D-2017,201-D-2017
1-P-1991 | 1 | 04/24/2000 | Crack Sealing | Clean and Fill - 3719 sealant touch up (Passing Lane)
1-D-2006 | 1 | 06/26/2012 | Section Ends | Replaced with Section(s) 1-D-2012
1-D-1991 | 1 | 08/30/1991 | Section Constructed | New Cell
1-P-1991 | 1 | 08/30/1991 | Section Constructed | New Cell
1-D-1991 | 1 | 04/04/1998 | Crack Sealing | """Crafco 522 sealant used with a 3/4"""" route. Comparison Cell-3."""
1-D-2012 | 1 | 06/27/2012 | Section Constructed | Constructed on Section 1-D-2006
1-D-2006 | 1 | 07/07/2006 | Section Constructed | Constructed on Section 1-D-1991
1-D-1991 | 1 | 04/24/2000 | Crack Sealing | Clean and Fill - 3723 sealant touch up (Driving Lane)
1-P-1991 | 1 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
1-P-2012 | 1 | 06/27/2012 | Section Constructed | Constructed on Section 1-P-1991
1-P-2012 | 1 | 07/25/2017 | Section Ends | Replaced with Section(s) 101-P-2017,201-P-2017
2-D-1991 | 2 | 08/14/2003 | Section Ends | Replaced with Section(s) 2-D-2003
2-P-2008 | 2 | 07/15/2019 | Crack Sealing | Longitudinal joints and some transverse cracks
2-D-1991 | 2 | 04/24/2000 | Crack Sealing | Clean and Fill - 500 ft of 3723 sealant (Driving Lane)
2-D-2008 | 2 | 06/01/2022 | Section Ends | Section Ends
2-D-2003 | 2 | 08/15/2003 | Section Constructed | Constructed on Section 2-D-1991
2-D-2008 | 2 | 07/15/2019 | Crack Sealing | Longitudinal joints and some transverse cracks
2-P-1991 | 2 | 04/24/2000 | Crack Sealing | Clean and Fill - 500 ft of 3719 sealant (Passing Lane)
2-D-1991 | 2 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
2-P-1991 | 2 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
2-P-1991 | 2 | 08/14/2003 | Section Ends | Replaced with Section(s) 2-P-2003
2-P-2008 | 2 | 07/15/2008 | Section Constructed | Constructed on Section 2-P-2003
2-D-1991 | 2 | 08/13/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1111+60
2-P-2003 | 2 | 08/15/2003 | Section Constructed | Constructed on Section 2-P-1991
2-D-2008 | 2 | 07/15/2008 | Section Constructed | Constructed on Section 2-D-2003
2-P-1991 | 2 | 08/30/1991 | Section Constructed | New Cell
2-P-2003 | 2 | 07/14/2008 | Section Ends | Replaced with Section(s) 2-P-2008
2-D-1991 | 2 | 08/30/1991 | Section Constructed | New Cell
2-D-2003 | 2 | 07/14/2008 | Section Ends | Replaced with Section(s) 2-D-2008
2-P-2008 | 2 | 06/01/2022 | Section Ends | Section Ends
3-P-2008 | 3 | 07/15/2008 | Section Constructed | Constructed on Section 3-P-1990
3-D-2008 | 3 | 12/03/2018 | Preservation testing
3-P-2008 | 3 | 07/16/2019 | Crack Sealing | Longitudinal Joints and some transverse cracks
3-P-2008 | 3 | 06/01/2022 | Section Ends | Section Ends
3-D-1990 | 3 | 08/13/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1114+62.5
3-D-1990 | 3 | 07/14/2008 | Section Ends | Replaced with Section(s) 3-D-2008
3-D-2008 | 3 | 07/16/2019 | Crack Sealing | Longitudinal Joints and some transverse cracks
3-P-1990 | 3 | 11/14/1990 | Section Constructed | New Cell
3-D-2008 | 3 | 07/15/2008 | Section Constructed | Constructed on Section 3-D-1990
3-D-1990 | 3 | 11/14/1990 | Section Constructed | New Cell
3-D-2008 | 3 | 06/01/2022 | Section Ends | Section Ends
3-P-1990 | 3 | 07/14/2008 | Section Ends | Replaced with Section(s) 3-P-2008
4-D-1991 | 4 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
4-D-1991 | 4 | 08/17/2003 | Section Ends | Replaced with Section(s) 4-D-2003
4-D-2008 | 4 | 06/01/2022 | Section Ends | Section Ends
4-D-1991 | 4 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
4-P-2008 | 4 | 07/09/2008 | Section Constructed | Constructed on Section 4-P-2003
4-D-2008 | 4 | 07/09/2008 | Section Constructed | Constructed on Section 4-D-2003
4-P-1991 | 4 | 04/24/2000 | Crack Sealing | Clean and Fill - 400 ft of 3723 sealant (Passing Lane)
4-P-1991 | 4 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
4-D-2008 | 4 | 08/03/2010 | Bituminous Patches | Two- six by six foot patches to remedy frost heave due to moisture intrusion over winter
4-D-1991 | 4 | 08/13/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1120+34.5
4-P-1991 | 4 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
4-D-1991 | 4 | 08/28/1991 | Section Constructed | New Cell
4-D-2003 | 4 | 07/08/2008 | Section Ends | Replaced with Section(s) 4-D-2008
4-P-1991 | 4 | 08/28/1991 | Section Constructed | New Cell
4-P-1991 | 4 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
4-D-2008 | 4 | 07/16/2019 | Crack Sealing | Longitudinal joints and some transverse cracking
4-P-2003 | 4 | 07/08/2008 | Section Ends | Replaced with Section(s) 4-P-2008
4-D-1991 | 4 | 04/24/2000 | Crack Sealing | Clean and Fill 400 ft of 3719 sealant (Driving Lane)
4-D-1991 | 4 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
4-P-1991 | 4 | 08/17/2003 | Section Ends | Replaced with Section(s) 4-P-2003
4-P-2003 | 4 | 08/18/2003 | Section Constructed | Constructed on Section 4-P-1991
4-D-2003 | 4 | 08/18/2003 | Section Constructed | Constructed on Section 4-D-1991
4-P-2008 | 4 | 07/16/2019 | Crack Sealing | Longitudinal joints and some transverse cracks
4-P-2008 | 4 | 06/01/2022 | Section Ends | Section Ends
14-D-1991 | 14 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
14-P-1991 | 14 | 05/14/1991 | Section Constructed | New Cell
14-D-1991 | 14 | 05/14/1991 | Section Constructed | New Cell
14-P-1991 | 14 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
14-D-1991 | 14 | 04/24/2000 | Crack Sealing | Clean and Fill -300 ft of 3719 sealant (Driving Lane)
14-D-1991 | 14 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
14-D-1991 | 14 | 05/07/2008 | Section Ends | Replaced with Section(s) 114-D-2008,214-D-2008,314-D-2008,414-D-2008,514-D-2008,614-D-2008,714-D-2008,814-D-2008,914-D-2008
14-D-1991 | 14 | 09/09/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1192+90
14-P-1991 | 14 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
14-D-1991 | 14 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
14-P-1991 | 14 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
14-P-1991 | 14 | 04/24/2000 | Crack Sealing | Clean and Fill - 300 ft of 3723 sealant (Passing Lane)
14-P-1991 | 14 | 05/07/2008 | Section Ends | Replaced with Section(s) 114-P-2008,214-P-2008,314-P-2008,414-P-2008,514-P-2008,614-P-2008,714-P-2008,814-P-2008,914-P-2008
15-P-2003 | 15 | 08/18/2003 | Section Constructed | Constructed on Section 15-P-1991
15-D-2004 | 15 | 09/16/2008 | Section Ends | Replaced with Section(s) 15-D-2008
15-P-2008 | 15 | 09/17/2008 | Section Constructed | Constructed on Section 15-P-2004
15-P-2008 | 15 | 07/25/2017 | Section Ends | Replaced with Section(s) 115-P-2017,215-P-2017
15-P-1991 | 15 | 08/17/2003 | Section Ends | Replaced with Section(s) 15-P-2003
15-D-2004 | 15 | 08/08/2004 | Section Constructed | Constructed on Section 15-D-2003
15-D-1991 | 15 | 04/24/2000 | Crack Sealing | Clean and Fill -100 ft of 3723 sealant (Driving Lane)
15-D-1991 | 15 | 09/09/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1196+50
15-D-2008 | 15 | 09/17/2008 | Section Constructed | Constructed on Section 15-D-2004
15-D-1991 | 15 | 05/14/1991 | Section Constructed | New Cell
15-P-1991 | 15 | 04/24/2000 | Crack Sealing | Clean and Fill - 100 ft of 3719 sealant (Passing Lane)
15-P-1991 | 15 | 07/16/2003 | Transverse crack leveling | Level transverse cracks with MiniMac Slurry in both lanes by Mn/DOT
15-D-1991 | 15 | 07/16/2003 | Transverse crack leveling | Level transverse cracks with MiniMac Slurry in both lanes by Mn/DOT
15-D-2003 | 15 | 08/18/2003 | Section Constructed | Constructed on Section 15-D-1991
15-D-2003 | 15 | 08/07/2004 | Section Ends | Replaced with Section(s) 15-D-2004
15-P-2004 | 15 | 08/08/2004 | Section Constructed | Constructed on Section 15-P-2003
15-D-2008 | 15 | 07/25/2017 | Section Ends | Replaced with Section(s) 115-D-2017,215-D-2017
15-P-2004 | 15 | 09/16/2008 | Section Ends | Replaced with Section(s) 15-P-2008
15-P-1991 | 15 | 05/14/1991 | Section Constructed | New Cell
15-D-1991 | 15 | 08/17/2003 | Section Ends | Replaced with Section(s) 15-D-2003
15-P-2003 | 15 | 08/07/2004 | Section Ends | Replaced with Section(s) 15-P-2004
15-D-1991 | 15 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
15-P-1991 | 15 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
16-P-1990 | 16 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
16-D-2008 | 16 | 06/26/2008 | Section Constructed | Constructed on Section 16-D-2004
16-P-1990 | 16 | 04/24/2000 | Crack Sealing | Clean and Fill - 3719 sealant touch up (Passing Lane)
16-D-2004 | 16 | 08/08/2004 | Section Constructed | Constructed on Section 16-D-1990
16-D-1990 | 16 | 04/24/2000 | Crack Sealing | Clean and Fill - 3723 sealant touch up (Driving Lane)
16-D-1990 | 16 | 05/13/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
16-P-2016 | 16 | 08/08/2016 | Section Constructed | Constructed on Section 16-P-2008
16-D-1990 | 16 | 04/04/1998 | Crack Sealing | """Crafco 522 sealant used with a 3/4"""" route. Comparison Cell-17."""
16-D-1990 | 16 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
16-D-1990 | 16 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
16-P-1990 | 16 | 08/07/2004 | Section Ends | Replaced with Section(s) 16-P-2004
16-P-2008 | 16 | 06/26/2008 | Section Constructed | Constructed on Section 16-P-2004
16-D-2016 | 16 | 10/24/2019 | crack seal | 35 feet of edge line crack seal (ran out of sealant)
16-P-1990 | 16 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
16-D-1990 | 16 | 08/31/1990 | Section Constructed | New Cell
16-D-1990 | 16 | 08/10/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch
16-P-1990 | 16 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
16-P-2004 | 16 | 06/25/2008 | Section Ends | Replaced with Section(s) 16-P-2008
16-D-2016 | 16 | 06/01/2022 | Secton Ends | Secton Ends
16-P-1990 | 16 | 04/04/1998 | Crack Sealing | """Crafco 522 sealant used with a 3/4"""" route. Comparison Cell-17."""
16-P-2004 | 16 | 08/08/2004 | Section Constructed | Constructed on Section 16-P-1990
16-D-2008 | 16 | 08/07/2016 | Section Ends | Replaced with Section(s) 16-D-2016
16-P-2008 | 16 | 08/07/2016 | Section Ends | Replaced with Section(s) 16-P-2016
16-D-2016 | 16 | 08/08/2016 | Section Constructed | Constructed on Section 16-D-2008
16-P-2016 | 16 | 10/24/2019 | crack seal | 500 feet of centerline crack seal
16-P-1990 | 16 | 08/31/1990 | Section Constructed | New Cell
16-D-1990 | 16 | 08/07/2004 | Section Ends | Replaced with Section(s) 16-D-2004
16-D-2004 | 16 | 06/25/2008 | Section Ends | Replaced with Section(s) 16-D-2008
16-P-2016 | 16 | 06/01/2022 | Secton Ends | Secton Ends
17-D-2004 | 17 | 06/25/2008 | Section Ends | Replaced with Section(s) 17-D-2008
17-D-2008 | 17 | 06/26/2008 | Section Constructed | Constructed on Section 17-D-2004
17-P-2008 | 17 | 08/07/2016 | Section Ends | Replaced with Section(s) 17-P-2016
17-P-2016 | 17 | 06/01/2022 | Secton Ends | Secton Ends
17-D-1990 | 17 | 08/31/1990 | Section Constructed | New Cell
17-P-2004 | 17 | 08/08/2004 | Section Constructed | Constructed on Section 17-P-1990
17-D-2016 | 17 | 06/01/2022 | Secton Ends | Secton Ends
17-P-1990 | 17 | 08/31/1990 | Section Constructed | New Cell
17-D-1990 | 17 | 08/10/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch
17-P-1990 | 17 | 08/07/2004 | Section Ends | Replaced with Section(s) 17-P-2004
17-D-2008 | 17 | 08/07/2016 | Section Ends | Replaced with Section(s) 17-D-2016
17-D-2016 | 17 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
17-P-2016 | 17 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, centerline construction joint
17-D-2004 | 17 | 08/08/2004 | Section Constructed | Constructed on Section 17-D-1990
17-P-2004 | 17 | 06/25/2008 | Section Ends | Replaced with Section(s) 17-P-2008
17-P-2008 | 17 | 06/26/2008 | Section Constructed | Constructed on Section 17-P-2004
17-P-2016 | 17 | 08/08/2016 | Section Constructed | Constructed on Section 17-P-2008
17-D-1990 | 17 | 08/07/2004 | Section Ends | Replaced with Section(s) 17-D-2004
17-D-2016 | 17 | 08/08/2016 | Section Constructed | Constructed on Section 17-D-2008
18-P-1990 | 18 | 04/24/2000 | Crack Sealing | Clean and Fill - 600 ft of 3723 sealant (Passing Lane)
18-D-1990 | 18 | 04/24/2000 | Crack Sealing | Clean and Fill -600 ft of 3719 sealant (Driving Lane)
18-P-1990 | 18 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
18-D-2003 | 18 | 08/24/2008 | Section Ends | Replaced with Section(s) 18-D-2008
18-D-2008 | 18 | 08/25/2008 | Section Constructed | Constructed on Section 18-D-2003
18-D-2016 | 18 | 08/08/2016 | Section Constructed | Constructed on Section 18-D-2014
18-D-2016 | 18 | 08/06/2020 | patching | pothole patched in right wheel path, 2 sq. ft.
18-D-1990 | 18 | 08/31/1990 | Section Constructed | New Cell
18-D-1990 | 18 | 08/19/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch
18-P-2003 | 18 | 08/24/2008 | Section Ends | Replaced with Section(s) 18-P-2008
18-D-2008 | 18 | 07/15/2014 | Section Ends | Replaced with Section(s) 18-D-2014
18-D-2016 | 18 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
18-P-2014 | 18 | 08/07/2016 | Section Ends | Replaced with Section(s) 18-P-2016
18-P-1990 | 18 | 08/31/1990 | Section Constructed | New Cell
18-P-1990 | 18 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
18-D-1990 | 18 | 08/17/2003 | Section Ends | Replaced with Section(s) 18-D-2003
18-P-1990 | 18 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
18-P-2008 | 18 | 08/25/2008 | Section Constructed | Constructed on Section 18-P-2003
18-D-2014 | 18 | 07/16/2014 | Section Constructed | Constructed on Section 18-D-2008
18-P-2016 | 18 | 08/08/2016 | Section Constructed | Constructed on Section 18-P-2014
18-D-2016 | 18 | 06/03/2021 | HMA Mill and Fill | "577' 2"" Patch from transition with cell 17 (station 1211+54) to transition with cell 19 (station 1217+31)"
18-D-1990 | 18 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
18-P-1990 | 18 | 08/17/2003 | Section Ends | Replaced with Section(s) 18-P-2003
18-P-2003 | 18 | 08/18/2003 | Section Constructed | Constructed on Section 18-P-1990
18-D-2014 | 18 | 08/07/2016 | Section Ends | Replaced with Section(s) 18-D-2016
18-P-2016 | 18 | 10/24/2019 | crack sealing | 500 feet of longitudinal crack seal, centerline construction joint
18-D-2016 | 18 | 06/01/2022 | Secton Ends | Secton Ends
18-D-1990 | 18 | 06/17/2003 | Transverse crack leveling | Level transverse cracks with Crafco PolyPatch mastic (Both lanes - half cell Crafco/ half cell Deery)
18-D-1990 | 18 | 06/18/2003 | Transverse crack leveling | Level transverse cracks with Deery Level-N-Go mastic (Both lanes - half cell Crafco/ half cell Deery)
18-D-2003 | 18 | 08/18/2003 | Section Constructed | Constructed on Section 18-D-1990
18-P-2008 | 18 | 07/15/2014 | Section Ends | Replaced with Section(s) 18-P-2014
18-P-2014 | 18 | 07/16/2014 | Section Constructed | Constructed on Section 18-P-2008
18-D-2016 | 18 | 02/24/2020 | Bituminous Patch (Perma) 4 locations | "Patched 4 pothole areas on western end with PermaPatch. Depth was 2"" for all patches. Total area patched = 4.5 ft2"
18-P-2016 | 18 | 06/01/2022 | Secton Ends | Secton Ends
19-P-1990 | 19 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
19-P-2003 | 19 | 08/18/2003 | Section Constructed | Constructed on Section 19-P-1990
19-P-2014 | 19 | 07/16/2014 | Section Constructed | Constructed on Section 19-P-2008
19-P-2016 | 19 | 10/24/2019 | crack seal | 450 feet of longitudinal crack seal, centerline construction joint
19-D-1990 | 19 | 08/17/2003 | Section Ends | Replaced with Section(s) 19-D-2003
19-P-2008 | 19 | 06/19/2008 | Section Constructed | Constructed on Section 19-P-2003
19-D-2008 | 19 | 07/15/2014 | Section Ends | Replaced with Section(s) 19-D-2014
19-P-2016 | 19 | 06/01/2022 | Secton Ends | Secton Ends
19-D-2016 | 19 | 06/01/2022 | Secton Ends | Secton Ends
19-P-1990 | 19 | 08/17/2003 | Section Ends | Replaced with Section(s) 19-P-2003
19-D-2014 | 19 | 07/16/2014 | Section Constructed | Constructed on Section 19-D-2008
19-D-1990 | 19 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
19-P-2008 | 19 | 07/15/2014 | Section Ends | Replaced with Section(s) 19-P-2014
19-P-2016 | 19 | 08/08/2016 | Section Constructed | Constructed on Section 19-P-2014
19-P-1990 | 19 | 09/20/1990 | Section Constructed | New Cell
19-D-2008 | 19 | 06/19/2008 | Section Constructed | Constructed on Section 19-D-2003
19-D-2014 | 19 | 08/07/2016 | Section Ends | Replaced with Section(s) 19-D-2016
19-P-2014 | 19 | 08/07/2016 | Section Ends | Replaced with Section(s) 19-P-2016
19-D-2016 | 19 | 08/08/2016 | Section Constructed | Constructed on Section 19-D-2014
19-D-1990 | 19 | 09/20/1990 | Section Constructed | New Cell
19-D-1990 | 19 | 08/10/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1222+41
19-D-2003 | 19 | 08/18/2003 | Section Constructed | Constructed on Section 19-D-1990
19-D-2003 | 19 | 06/18/2008 | Section Ends | Replaced with Section(s) 19-D-2008
19-P-2003 | 19 | 06/18/2008 | Section Ends | Replaced with Section(s) 19-P-2008
19-D-2016 | 19 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
19-D-1990 | 19 | 04/24/2000 | Crack Sealing | Clean and Fill -800 ft of 3719 sealant (Driving Lane)
19-P-1990 | 19 | 04/24/2000 | Crack Sealing | Clean and Fill -800 ft of 3723 sealant (Passing Lane)
20-P-1990 | 20 | 09/10/1990 | Section Constructed | New Cell
20-D-1999 | 20 | 08/17/2003 | Section Ends | Replaced with Section(s) 20-D-2003
20-P-2016 | 20 | 10/24/2019 | crack seal | 460 feet of longitudinal crack seal, centerline construction joint
20-D-1990 | 20 | 07/17/1999 | Section Ends | Replaced with Section(s) 20-D-1999
20-P-1999 | 20 | 07/18/1999 | Section Constructed | Constructed on Section 20-P-1990
20-D-2003 | 20 | 05/08/2008 | Section Ends | Replaced with Section(s) 20-D-2008
20-D-2008 | 20 | 09/27/2016 | Section Ends | Replaced with Section(s) 20-D-2016
20-D-1990 | 20 | 09/10/1990 | Section Constructed | New Cell
20-D-1999 | 20 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
20-P-2003 | 20 | 08/18/2003 | Section Constructed | Constructed on Section 20-P-1999
20-P-2003 | 20 | 05/08/2008 | Section Ends | Replaced with Section(s) 20-P-2008
20-D-2016 | 20 | 06/01/2022 | Secton Ends | Secton Ends
20-D-1999 | 20 | 07/18/1999 | Section Constructed | Constructed on Section 20-D-1990
20-P-2008 | 20 | 09/27/2016 | Section Ends | Replaced with Section(s) 20-P-2016
20-D-2016 | 20 | 09/28/2016 | Section Constructed | Constructed on Section 20-D-2008
20-D-1990 | 20 | 06/15/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1222+91
20-P-1990 | 20 | 07/17/1999 | Section Ends | Replaced with Section(s) 20-P-1999
20-D-1999 | 20 | 04/24/2000 | Crack Sealing | Clean and Fill -20 ft of 3723 sealant (Driving Lane)
20-P-1999 | 20 | 04/24/2000 | Crack Sealing | Clean and Fill - 20 ft of 3719 sealant (Passing Lane)
20-P-1999 | 20 | 08/17/2003 | Section Ends | Replaced with Section(s) 20-P-2003
20-P-2008 | 20 | 05/09/2008 | Section Constructed | Constructed on Section 20-P-2003
20-D-2008 | 20 | 05/09/2008 | Section Constructed | Constructed on Section 20-D-2003
20-P-2016 | 20 | 09/28/2016 | Section Constructed | Constructed on Section 20-P-2008
20-P-2016 | 20 | 06/01/2022 | Secton Ends | Secton Ends
20-P-1999 | 20 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
20-D-2003 | 20 | 08/18/2003 | Section Constructed | Constructed on Section 20-D-1999
20-D-2016 | 20 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
21-P-1990 | 21 | 08/17/2003 | Section Ends | Replaced with Section(s) 21-P-2003
21-D-2016 | 21 | 09/28/2016 | Section Constructed | Constructed on Section 21-D-2008
21-D-1990 | 21 | 08/17/2003 | Section Ends | Replaced with Section(s) 21-D-2003
21-P-2003 | 21 | 08/18/2003 | Section Constructed | Constructed on Section 21-P-1990
21-D-2008 | 21 | 09/27/2016 | Section Ends | Replaced with Section(s) 21-D-2016
21-P-2016 | 21 | 06/01/2022 | Secton Ends | Secton Ends
21-D-2003 | 21 | 06/12/2008 | Section Ends | Replaced with Section(s) 21-D-2008
21-P-2003 | 21 | 06/12/2008 | Section Ends | Replaced with Section(s) 21-P-2008
21-P-2008 | 21 | 06/13/2008 | Section Constructed | Constructed on Section 21-P-2003
21-D-1990 | 21 | 09/12/1990 | Section Constructed | New Cell
21-D-1990 | 21 | 04/24/2000 | Crack Sealing | Clean and Fill 450 ft of 3723 sealant (Driving Lane)
21-D-1990 | 21 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
21-D-2008 | 21 | 06/13/2008 | Section Constructed | Constructed on Section 21-D-2003
21-P-2008 | 21 | 09/27/2016 | Section Ends | Replaced with Section(s) 21-P-2016
21-D-2016 | 21 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
21-P-1990 | 21 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
21-D-2016 | 21 | 06/01/2022 | Secton Ends | Secton Ends
21-P-1990 | 21 | 09/12/1990 | Section Constructed | New Cell
21-P-1990 | 21 | 04/24/2000 | Crack Sealing | Clean and Fill - 450 ft of 3719 sealant (Passing Lane)
21-D-2003 | 21 | 08/18/2003 | Section Constructed | Constructed on Section 21-D-1990
21-D-1990 | 21 | 09/09/2001 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1230+71
21-P-2016 | 21 | 09/28/2016 | Section Constructed | Constructed on Section 21-P-2008
21-P-2016 | 21 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, centerline construction joint
22-D-1990 | 22 | 08/04/1990 | Section Constructed | New Cell
22-P-1990 | 22 | 04/24/2000 | Crack Sealing | Clean and Fill - 450 ft of 3723 sealant (Passing Lane)
22-D-2016 | 22 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, shoulder construction joint
22-D-2016 | 22 | 06/01/2022 | Secton Ends | Secton Ends
22-P-2003 | 22 | 08/18/2003 | Section Constructed | Constructed on Section 22-P-1990
22-D-2008 | 22 | 06/16/2008 | Section Constructed | Constructed on Section 22-D-2003
22-P-1990 | 22 | 08/17/2003 | Section Ends | Replaced with Section(s) 22-P-2003
22-D-2016 | 22 | 09/28/2016 | Section Constructed | Constructed on Section 22-D-2008
22-D-1990 | 22 | 08/10/1999 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA
22-D-1990 | 22 | 08/17/2003 | Section Ends | Replaced with Section(s) 22-D-2003
22-P-2008 | 22 | 09/27/2016 | Section Ends | Replaced with Section(s) 22-P-2016
22-D-2008 | 22 | 09/27/2016 | Section Ends | Replaced with Section(s) 22-D-2016
22-D-1990 | 22 | 04/24/2000 | Crack Sealing | Clean and Fill 450 ft of 3719 sealant (Driving Lane)
22-P-1990 | 22 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
22-D-2003 | 22 | 08/18/2003 | Section Constructed | Constructed on Section 22-D-1990
22-D-2003 | 22 | 06/15/2008 | Section Ends | Replaced with Section(s) 22-D-2008
22-P-2003 | 22 | 06/15/2008 | Section Ends | Replaced with Section(s) 22-P-2008
22-P-2016 | 22 | 09/28/2016 | Section Constructed | Constructed on Section 22-P-2008
22-P-2016 | 22 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, centerline construction joint
22-P-2016 | 22 | 06/01/2022 | Secton Ends | Secton Ends
22-P-1990 | 22 | 08/04/1990 | Section Constructed | New Cell
22-D-1990 | 22 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
22-P-2008 | 22 | 06/16/2008 | Section Constructed | Constructed on Section 22-P-2003
23-D-1999 | 23 | 07/18/1999 | Section Constructed | Constructed on Section 23-D-1990
23-D-1999 | 23 | 04/24/2000 | Crack Sealing | Clean and Fill -20 ft of 3719 sealant (Driving Lane)
23-P-2008 | 23 | 06/23/2008 | Section Constructed | Constructed on Section 23-P-1999
23-D-2016 | 23 | 06/01/2022 | Secton Ends | Secton Ends
23-P-1999 | 23 | 06/22/2008 | Section Ends | Replaced with Section(s) 23-P-2008
23-P-2016 | 23 | 10/24/2019 | crack seal | 500 feet of longitudinal crack seal, centerline construction joint
23-D-1990 | 23 | 06/15/1998 | Test Pit | Test pit done in the driving lane to investigate mainline rutting resulting in a (3x10) patch at STA 1240+35
23-P-1999 | 23 | 07/18/1999 | Section Constructed | Constructed on Section 23-P-1990
23-D-1999 | 23 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
23-D-1999 | 23 | 06/22/2008 | Section Ends | Replaced with Section(s) 23-D-2008
23-D-2008 | 23 | 06/23/2008 | Section Constructed | Constructed on Section 23-D-1999
23-D-2016 | 23 | 06/03/2021 | HMA Mill and Fill Patches | "2"" Mill and Fill patches 104' by 12' on East end and 71.5' by 12' on West end. Work performed by CAT."
23-D-1990 | 23 | 10/10/1990 | Section Constructed | New Cell
23-P-2008 | 23 | 09/27/2016 | Section Ends | Replaced with Section(s) 23-P-2016
23-P-2016 | 23 | 09/28/2016 | Section Constructed | Constructed on Section 23-P-2008
23-P-1990 | 23 | 10/10/1990 | Section Constructed | New Cell
23-P-1990 | 23 | 07/17/1999 | Section Ends | Replaced with Section(s) 23-P-1999
23-D-2016 | 23 | 09/28/2016 | Section Constructed | Constructed on Section 23-D-2008
23-D-2016 | 23 | 10/24/2019 | crack seal | 740 feet of longitudinal crack seal, 500 feet of shoulder construction joint, 240 feet of driving lane longitudinal cracks
23-P-2016 | 23 | 06/01/2022 | Secton Ends | Secton Ends
23-D-1990 | 23 | 07/17/1999 | Section Ends | Replaced with Section(s) 23-D-1999
23-P-1999 | 23 | 04/24/2000 | Crack Sealing | Clean and Fill - -20 ft of 3723 sealant (Passing Lane)
23-P-1999 | 23 | 05/21/2003 | Crack Sealing | Reseal transverse cracks both lanes with crumb-rubber (3719) sealant
23-D-2008 | 23 | 09/27/2016 | Section Ends | Replaced with Section(s) 23-D-2016
50-D-1991 | 50 | 08/30/1991 | Section Constructed | New Cell
50-P-1991 | 50 | 08/30/1991 | Section Constructed | New Cell
50-D-1997 | 50 | 04/24/2000 | Crack Sealing | Clean and Fill - 12 ft of 3723 sealant (Driving Lane)
50-D-1997 | 50 | 07/15/1997 | Section Constructed | Constructed on Section 50-D-1991
50-P-1997 | 50 | 04/24/2000 | Crack Sealing | Clean and Fill - 12 ft of 3719 sealant (Passing Lane)
50-D-1991 | 50 | 07/14/1997 | Section Ends | Replaced with Section(s) 50-D-1997
50-D-1997 | 50 | 05/01/2008 | Section Ends | Replaced with Section(s)
50-P-1997 | 50 | 07/15/1997 | Section Constructed | Constructed on Section 50-P-1991
50-P-1997 | 50 | 05/01/2008 | Section Ends | Replaced with Section(s)
50-P-1991 | 50 | 07/14/1997 | Section Ends | Replaced with Section(s) 50-P-1997
51-D-1991 | 51 | 08/30/1991 | Section Constructed | New Cell
51-P-1991 | 51 | 08/30/1991 | Section Constructed | New Cell
51-P-1997 | 51 | 07/15/1997 | Section Constructed | Constructed on Section 51-P-1991
51-P-1997 | 51 | 05/01/2008 | Section Ends | Replaced with Section(s)
51-D-1991 | 51 | 07/14/1997 | Section Ends | Replaced with Section(s) 51-D-1997
51-D-1997 | 51 | 07/15/1997 | Section Constructed | Constructed on Section 51-D-1991
51-D-1997 | 51 | 05/01/2008 | Section Ends | Replaced with Section(s)
51-P-1991 | 51 | 07/14/1997 | Section Ends | Replaced with Section(s) 51-P-1997
51-D-1997 | 51 | 04/24/2000 | Crack Sealing | Clean and Fill - 12 ft of 3723 sealant (Driving Lane)
51-P-1997 | 51 | 04/24/2000 | Crack Sealing | Clean and Fill - 12 ft of 3719 sealant (Passing Lane)
70-P-2010 | 70 | 04/19/2010 | Section Constructed | Constructed on Section 97-P-1997
70-P-2010 | 70 | 06/01/2022 | Section Ends | Section Ends
70-D-2010 | 70 | 04/19/2010 | Section Constructed | Constructed on Section 97-D-1997
70-D-2010 | 70 | 06/01/2022 | Section Ends | Section Ends
70-P-2010 | 70 | 06/03/2021 | HMA Patch | "15'2"" by 12'8"" HMA Patch to replace delaminated overlay and underlying cracked concrete. Lower lift placed and rolled by MnROAD, Upper lifted paved by CAT. "
70-D-2010 | 70 | 06/03/2021 | HMA Patch | "15'2"" by 12'8"" HMA Patch to replace delaminated overlay and underlying cracked concrete. Lower lift placed and rolled by MnROAD, Upper lifted paved by CAT. "
93-P-1990 | 93 | 10/05/1990 | Section Constructed | New Cell
93-P-1990 | 93 | 10/02/1997 | Section Ends | Replaced with Section(s) 93-P-1997
101-D-2017 | 101 | 07/26/2017 | Section Constructed | Constructed on Section 1-D-2012
101-P-2017 | 101 | 08/06/2020 | patching | two patches made with Crafco cold patch 2.5 square feet
101-P-2017 | 101 | 07/26/2017 | Section Constructed | Constructed on Section 1-P-2012
101-D-2017 | 101 | 08/06/2020 | patching | 4 patches, 4.3 square feet total, crafco cold patch
101-D-2017 | 101 | 06/01/2022 | Section Ends | Section Ends
101-P-2017 | 101 | 06/01/2022 | Section Ends | Section Ends
101-P-2017 | 101 | 03/21/2021 | Mastic patches (15) | 15 Mastic Patches for a total of 118 square feet
106-P-2008 | 106 | 08/02/2011 | Section Ends | Replaced with Section(s) 306-P-2011
106-D-2008 | 106 | 08/02/2011 | Section Ends | Replaced with Section(s) 306-D-2011
106-D-2008 | 106 | 08/25/2008 | Section Constructed | Constructed on Section 6-D-1991
106-P-2008 | 106 | 08/25/2008 | Section Constructed | Constructed on Section 6-P-1991
115-D-2017 | 115 | 06/03/2021 | HMA Mill and Fill Patch | "14' 2"" mill and overlay patch across driving and passing lanes on West end against Cell 114."
115-P-2017 | 115 | 06/01/2022 | Section Ends | Section Ends
115-D-2017 | 115 | 06/01/2022 | Section Ends | Section Ends
115-P-2017 | 115 | 06/03/2021 | HMA Mill and Fill Patch | "14' 2"" mill and overlay patch across driving and passing lanes on West end against Cell 114."
115-P-2017 | 115 | 07/26/2017 | Section Constructed | Constructed on Section 15-P-2008
115-D-2017 | 115 | 07/26/2017 | Section Constructed | Constructed on Section 15-D-2008
201-P-2017 | 201 | 06/01/2022 | Section Ends | Section Ends
201-D-2017 | 201 | 06/01/2022 | Section Ends | Section Ends
201-D-2017 | 201 | 07/26/2017 | Section Constructed | Constructed on Section 1-D-2012
201-P-2017 | 201 | 07/26/2017 | Section Constructed | Constructed on Section 1-P-2012
201-P-2017 | 201 | 03/29/2021 | Mastic Patches (14) | 14 patches totaling 108 square feet
206-P-2008 | 206 | 08/02/2011 | Section Ends | Replaced with Section(s) 406-P-2011
206-D-2008 | 206 | 08/02/2011 | Section Ends | Replaced with Section(s) 406-D-2011
206-D-2008 | 206 | 08/25/2008 | Section Constructed | Constructed on Section 6-D-1991
206-P-2008 | 206 | 08/25/2008 | Section Constructed | Constructed on Section 6-P-1991
215-P-2017 | 215 | 06/01/2022 | Section Ends | Section Ends
215-P-2017 | 215 | 07/26/2017 | Section Constructed | Constructed on Section 15-P-2008
215-D-2017 | 215 | 07/26/2017 | Section Constructed | Constructed on Section 15-D-2008
215-D-2017 | 215 | 06/01/2022 | Section Ends | Section Ends
905-D-2020 | 905 | 10/01/2020 | Section Constructed | Section Constructed
1005-D-2020 | 1005 | 10/01/2020 | Section Constructed | Full Depth HMA (One Lift) for all the lane
2201-D-2022 | 2201 | 10/12/2022 | Section Constructed | Section Constructed
2201-P-2022 | 2201 | 10/12/2022 | Section Constructed | Section Constructed
2202-D-2022 | 2202 | 10/12/2022 | Section Constructed | Section Constructed
2202-P-2022 | 2202 | 10/12/2022 | Section Constructed | Section Constructed
2203-D-2022 | 2203 | 10/12/2022 | Section Constructed | Section Constructed
2203-P-2022 | 2203 | 10/12/2022 | Section Constructed | Section Constructed
2204-D-2022 | 2204 | 10/12/2022 | Section Constructed | Section Constructed
2204-P-2022 | 2204 | 10/12/2022 | Section Constructed | Section Constructed
2205-P-2022 | 2205 | 10/12/2022 | Section Constructed | Section Constructed
2205-D-2022 | 2205 | 10/12/2022 | Section Constructed | Section Constructed
2206-D-2022 | 2206 | 10/12/2022 | Section Constructed | Section Constructed
2206-P-2022 | 2206 | 10/12/2022 | Section Constructed | Section Constructed
2207-D-2022 | 2207 | 10/12/2022 | Section Constructed | Section Constructed
2207-P-2022 | 2207 | 10/12/2022 | Section Constructed | Section Constructed
2208-D-2022 | 2208 | 10/12/2022 | Section Constructed | Section Constructed
2208-P-2022 | 2208 | 10/12/2022 | Section Constructed | Section Constructed
2228-D-2022 | 2228 | 10/12/2022 | Section Constructed | Section Constructed
2228-P-2022 | 2228 | 10/12/2022 | Section Constructed | Section Constructed
2229-D-2022 | 2229 | 10/12/2022 | Section Constructed | Section Constructed
2229-P-2022 | 2229 | 10/12/2022 | Section Constructed | Section Constructed
2230-D-2022 | 2230 | 10/12/2022 | Section Constructed | Section Constructed
2230-P-2022 | 2230 | 10/12/2022 | Section Constructed | Section Constructed
2231-P-2022 | 2231 | 10/12/2022 | Section Constructed | Section Constructed
2231-D-2022 | 2231 | 10/12/2022 | Section Constructed | Section Constructed
2232-D-2022 | 2232 | 10/12/2022 | Section Constructed | Section Constructed
2232-P-2022 | 2232 | 10/12/2022 | Section Constructed | Section Constructed
2233-D-2022 | 2233 | 10/12/2022 | Section Constructed | Section Constructed
2233-P-2022 | 2233 | 10/12/2022 | Section Constructed | Section Constructed
2234-D-2022 | 2234 | 10/12/2022 | Section Constructed | Section Constructed
2234-P-2022 | 2234 | 10/12/2022 | Section Constructed | Section Constructed
2235-P-2022 | 2235 | 10/12/2022 | Section Constructed | Section Constructed
2235-D-2022 | 2235 | 10/12/2022 | Section Constructed | Section Constructed
2236-D-2022 | 2236 | 10/12/2022 | Section Constructed | Section Constructed
2236-P-2022 | 2236 | 10/12/2022 | Section Constructed | Section Constructed
2237-P-2022 | 2237 | 10/12/2022 | Section Constructed | Section Constructed
2237-D-2022 | 2237 | 10/12/2022 | Section Constructed | Section Constructed
2238-P-2022 | 2238 | 10/12/2022 | Section Constructed | Section Constructed
2238-D-2022 | 2238 | 10/12/2022 | Section Constructed | Section Constructed
2239-D-2022 | 2239 | 10/12/2022 | Section Constructed | Section Constructed
2239-P-2022 | 2239 | 10/12/2022 | Section Constructed | Section Constructed

## TABLE DICTIONARY
TABLE_NAME | TABLE_ALIAS | TABLE_DESCRIPTION | CLASSIFICATION_NAME | CLASSIFICATION_DESCRIPTION
SECTION_TIMELINE_MV | Section Construction Timeline | Secton history of construction and other events at each. | Timeline | Contains construction history and timeline of the sections.

## DATA DICTIONARY
TABLE_NAME | FIELD_NAME | FIELD_ALIAS | FIELD_DESCRIPTION | UNITS | UNIT_SYSTEM
SECTION_TIMELINE_MV | SECTION_ID | Section ID | SECTION_ID is a unique id composite key to identify each cell construction event by CELL-LANE-YEAR of construction. From the CELL table.
SECTION_TIMELINE_MV | CELL | Cell | MnROAD Cell Number (test section). From CELL table.
SECTION_TIMELINE_MV | EVENT_DATE | Event Date | When the construction work was done. From CELL_HISTORY table DATE_WORK.
SECTION_TIMELINE_MV | EVENT_DESCRIPTION | Event Description | Description of the event done. From CELL_HISTORY table WORK_DONE.
SECTION_TIMELINE_MV | EVENT_COMMENTS | Event Comments | General notes and comments. From CELL_HISTORY table CELL_COMMENTS.